## Read me
Corrective-Action Tracker Template
Copyright (c) 2026 Integral Healthcare Solutions, Inc. (IHS). Free to use and adapt for your own organization's internal work. Do not sell it or republish it as your own. Provided as is, without warranty of any kind. IHS is a consulting firm, not a law firm; this is not legal advice. This is not a form issued or required by any accreditor or regulator, and using it does not guarantee any accreditation or regulatory outcome. Yellow rows are synthetic examples with fictional names; delete them before use.
What it is for | Tracks each corrective action from assignment to verified closure: what will change, who owns it, the due date, the evidence that it was done, and who checked that it worked. Rows past their due date and not closed turn red.
How to use it | 1. Delete the yellow example rows on the 'Corrective actions' sheet.
2. Give each action a unique Corrective-action ID and link the Finding ID from your Finding Log.
3. Write the action as a change someone can do and someone else can check ('Add a written mail-room hand-off step to Procedure GR-04'), not as an intention ('improve intake').
4. Assign one owner and a due date. The 'Past due' column calculates from today's date.
5. When the work is done, set Status to Pending verification, name the completion evidence, and have a second person verify it.
6. Close only after verification. Record the verifier and the date.
7. Check the 'Summary' sheet for counts by status and the number past due.
Columns
Corrective-action ID / Finding ID | Unique ID, and the finding it answers.
Corrective action | The specific change, written so it can be checked.
Owner / Due date | One accountable person and one date.
Status | Not started, In progress, Pending verification, Closed.
Completion evidence | The document, record or screenshot that shows the change was made.
Verified by / Date verified | A second person who confirmed the change works.
Past due | Calculated: YES when the due date has passed and Status is not Closed.
Notes | Anything the next reader needs.

## Corrective actions
Corrective-action ID | Finding ID | Corrective action | Owner | Due date | Status | Completion evidence | Verified by | Date verified | Past due | Notes
CA-001 | F-001 | Add a written mail-room hand-off step to Procedure GR-04 (fictional) and brief the two staff who open mail. | Example Owner B | 2026-02-27 | In progress |  |  |  |  | Draft procedure revision in review.
CA-002 | F-002 | Prepare and date the annual program evaluation report; adopt a calendar reminder in Policy QM-01 (fictional). | Example Owner A | 2026-03-13 | Not started
CA-003 | F-003 | Add a 30-day training check to the onboarding checklist for Example Health Plan (fictional). | Example Owner C | 2026-02-20 | Closed | Updated onboarding checklist v4 (fictional) | Example Owner A | 2026-02-24
Formulas:
Past due = IF(AND([Due date]<>"",[Status]<>"Closed",[Due date]<TODAY()),"YES","")

## Summary
Status | Actions
Not started
In progress
Pending verification
Closed
Past due